## Gantt Chart
Sprint List | Start | End | 2025-08-29 | 2025-08-31 | 2025-09-02 | 2025-09-04 | 2025-09-06 | 2025-09-08 | 2025-09-10 | 2025-09-12 | 2025-09-14 | 2025-09-16 | 2025-09-18 | 2025-09-20 | 2025-09-22 | 2025-09-25 | 2025-09-28 | 2025-09-30 | 2025-10-02 | 2025-10-04 | 2025-10-06 | 2025-10-07 | 2025-10-08 | 2025-10-10 | 2025-10-11 | 2025-10-13 | 2025-10-14 | 2025-10-16 | 2025-10-18 | 2025-10-20 | 2025-10-22 | 2025-10-24 | 2025-10-26 | 2025-10-28 | 2025-10-31 | 2025-11-02 | 2025-11-05 | 2025-11-06 | 2025-11-08 | 2025-11-10 | 2025-11-12 | 2025-11-14 | 2025-11-16 | 2025-11-17 | 2025-11-18 | 2025-11-19 | 2025-11-20 | 2025-11-21 | 2025-11-22 | 2025-11-23
Sprint 1: Login Module
Expected | 2025-08-29 | 2025-10-02
Actual | 2025-08-29 | 2025-10-02
Sprint 2: Chart of Accounts Module
Expected | 2025-10-02 | 2025-10-16
Actual | 2025-10-02 | 2025-10-16
Sprint 3: Journalizing & Ledger Module
Expected | 2025-10-16 | 2025-10-24
Actual | 2025-10-16 | 2025-10-24
Sprint 4: Financial Reports
Expected | 2025-10-24 | 2025-11-06
Actual | 2025-10-24 | 2025-11-06
Sprint 5: Ratios & Dashboard
Expected | 2025-11-06 | 2025-11-18
Actual | 2025-11-06 | 2025-11-18

## Help
Project Start Date | 2024-01-01
Days Per Column | 7
Instructions
1. Update "Project Start Date" and "Days Per Column" above.
2. Update the gantt chart rows with task names, start dates, and end dates.
3. The template will automatically fill the gantt chart bars.
Provided By
onlinegantt.com - Free Online Gantt Chart Software