## Gantt Chart
Task | Start | End | 2025-08-29 | 2025-08-31 | 2025-09-02 | 2025-09-04 | 2025-09-06 | 2025-09-08 | 2025-09-10 | 2025-09-12 | 2025-09-14 | 2025-09-16 | 2025-09-18 | 2025-09-20 | 2025-09-22 | 2025-09-25 | 2025-09-28 | 2025-09-29 | 2025-09-30 | 2025-10-01 | 2025-10-02 | 2025-10-03 | 2025-10-04 | 2025-10-06 | 2025-10-07 | 2025-10-09 | 2025-10-10 | 2025-10-12 | 2025-10-14 | 2025-10-16 | 2025-10-17 | 2025-10-18 | 2025-10-19 | 2025-10-20 | 2025-10-21 | 2025-10-22 | 2025-10-23 | 2025-10-24 | 2025-10-25 | 2025-10-26 | 2025-10-27 | 2025-10-29 | 2025-10-31 | 2025-11-01 | 2025-11-02 | 2025-11-03 | 2025-11-04 | 2025-11-05 | 2025-11-06 | 2025-11-07 | 2025-11-08 | 2025-11-09 | 2025-11-10 | 2025-11-11 | 2025-11-12 | 2025-11-13 | 2025-11-14 | 2025-11-15 | 2025-11-16 | 2025-11-17 | 2025-11-18 | 2025-11-19 | 2025-11-20 | 2025-11-21
Sprint 1
Expected | 2025-08-29 | 2025-09-09
1 - User Management | 2025-08-29 | 2025-09-09
Expected | 2025-09-08 | 2025-09-11
2 - Admin create users and assign roles | 2025-09-08 | 2025-09-11
Expected | 2025-09-01 | 2025-09-04
3 - Admin update user info | 2025-09-01 | 2025-09-04
Expected | 2025-09-08 | 2025-09-11
4 - Admin can Activate/Deactivate users | 2025-09-08 | 2025-09-11
Expected | 2025-08-28 | 2025-09-04
5 - Login once credentials created | 2025-08-28 | 2025-09-04
Expected | 2025-08-28 | 2025-09-04
6 - Display user login info on login page | 2025-08-28 | 2025-09-04
Expected | 2025-09-01 | 2025-09-05
7 - Login page U/I | 2025-09-01 | 2025-09-05
Expected | 2025-09-09 | 2025-09-16
8.1 - Create new user U/I | 2025-09-09 | 2025-09-16
Expected | 2025-09-23 | 2025-10-02
8.2 - Admin email new user request | 2025-09-23 | 2025-10-02
Expected | 2025-09-01 | 2025-09-05
9 - Forgot Password | 2025-09-01 | 2025-09-05
Expected | 2025-09-16 | 2025-09-18
10 - Password Requirement | 2025-09-16 | 2025-09-18
Expected | 2025-09-29 | 2025-10-02
11 - Can not use past password when reset | 2025-09-29 | 2025-10-16
Expected | 2025-09-09 | 2025-09-11
12 - Encrypt Passoword | 2025-09-09 | 2025-09-11
Expected | 2025-09-23 | 2025-10-02
13 - Max password attempts | 2025-09-23 | 2025-10-16
Expected | 2025-09-09 | 2025-09-18
14 - Store Info in Database | 2025-09-09 | 2025-09-18
Expected | 2025-09-29 | 2025-10-02
15 - Password expiration notification | 2025-09-29 | 2025-10-16
Expected | 2025-09-25 | 2025-09-30
16 - Admin report on users | 2025-09-25 | 2025-09-30
Expected | 2025-09-25 | 2025-10-02
18 - Admin receive report of all expired passwords | 2025-09-25 | 2025-10-02
Expected | 2025-09-23 | 2025-10-02
19 - Admin can send email for user | 2025-09-23 | 2025-10-02
Expected | 2025-09-02 | 2025-09-04
20 - Username credentials | 2025-09-02 | 2025-09-04
Sprint 2
Expected | 2025-10-02 | 2025-10-07
1 - Add, view, edit or deactivate accounts | 2025-10-02 | 2025-10-07
Expected | 2025-10-02 | 2025-10-07
2 - Account constraints | 2025-10-02 | 2025-10-07
Expected | 2025-10-02 | 2025-10-07
3 - Two decimals spaces for monetary values | 2025-10-02 | 2025-10-07
Expected | 2025-10-02 | 2025-10-07
4 - Monetary values formatted with commas when needed | 2025-10-02 | 2025-10-07
Expected | 2025-10-02 | 2025-10-07
5 - No decimals spaces or alphanumeric values in account numbers | 2025-10-02 | 2025-10-07
Expected | 2025-10-02 | 2025-10-07
6 - Can not deactivate account with balance greater than zero | 2025-10-02 | 2025-10-07
Expected | 2025-10-02 | 2025-10-09
7 - View either individual/report of accounts | 2025-10-02 | 2025-10-09
Expected | 2025-10-03 | 2025-10-08
8 - Search for account | 2025-10-03 | 2025-10-08
Expected | 2025-10-02 | 2025-10-06
9 - Name of logged in user displayed | 2025-10-02 | 2025-10-06
Expected | 2025-10-04 | 2025-10-16
10 - Logo must appear on each page | 2025-10-04 | 2025-10-16
Expected | 2025-10-05 | 2025-10-11
11 - Clicking each account in chart navigates to corresponding ledger | 2025-10-05 | 2025-10-23
Expected | 2025-10-07 | 2025-10-16
12 - Filter data in chart | 2025-10-07 | 2025-10-20
Expected | 2025-10-09 | 2025-10-14
13 - Pop up calendar | 2025-10-09 | 2025-10-14
Expected | 2025-10-10 | 2025-10-14
14 - Buttons to other services in header | 2025-10-10 | 2025-10-17
Expected | 2025-10-11 | 2025-10-16
15 - Event Log | 2025-10-11 | 2025-10-18
Expected | 2025-10-07 | 2025-10-14
16 - Consistent color and layout UI | 2025-10-07 | 2025-10-14
Expected | 2025-10-12 | 2025-10-14
17 - Built in tool tip | 2025-10-12 | 2025-10-14
Expected | 2025-10-12 | 2025-10-13
18 - Help button | 2025-10-12 | 2025-10-13
Expected | 2025-10-07 | 2025-10-14
19 - Manager functionality | 2025-10-07 | 2025-10-21
Expected | 2025-10-07 | 2025-10-14
20 - Accountant funcationality | 2025-10-07 | 2025-10-21
Sprint 3
Expected | 2025-10-16 | 2025-10-21
1 - Admin can add, view, edit, or deactivate accounts | 2025-10-16 | 2025-10-21
Expected | 2025-10-16 | 2025-10-21
2 - Admin can view event logs for each account in the chart of accounts | 2025-10-16 | 2025-10-21
Expected | 2025-10-16 | 2025-10-21
3 - Admin can send an email to the manager and the accountant user from the chart of accounts page. | 2025-10-16 | 2025-10-21
Expected | 2025-10-16 | 2025-10-21
4 - MGR can create journal entries using only accounts found in the chart of accounts | 2025-10-16 | 2025-10-21
Expected | 2025-10-16 | 2025-10-21
5 - MGR can approve or reject journal entries prepared by accountant. If journal entry submitted is rejected, manager must enter reason in the comment field | 2025-10-16 | 2025-10-21
Expected | 2025-10-16 | 2025-10-21
6 - MGR: Once journal entry is approved, the entry must be reflected in the ledger for the account | 2025-10-16 | 2025-10-21
Expected | 2025-10-16 | 2025-10-21
7 - MGR: Must be able to view all journal entries submitted for approval with pending approval status | 2025-10-16 | 2025-10-21
Expected | 2025-10-16 | 2025-10-21
8 - MGR Must be able to view all approved journal entries | 2025-10-16 | 2025-10-21
Expected | 2025-10-16 | 2025-10-21
9 - MGR: Must be able to view all rejected journal entries | 2025-10-16 | 2025-10-21
Expected | 2025-10-16 | 2025-10-21
10 - MGR: Must be able to filter journal entries displayed for pending, approved, and rejected categories by date | 2025-10-16 | 2025-10-21
Expected | 2025-10-16 | 2025-10-21
11 - MGR: Must be able to search a journal by account name, amount, or date | 2025-10-16 | 2025-10-25
Expected | 2025-10-16 | 2025-10-21
12 - MGR: Event logs | 2025-10-16 | 2025-10-25
Expected | 2025-10-16 | 2025-10-21
13 - MGR: Must be able to click an account name to go to the ledger of the account | 2025-10-16 | 2025-10-25
Expected | 2025-10-16 | 2025-10-21
14 - MGR: From the ledger page, must be able to click the post reference (PR) to go to the journal entry which created the account | 2025-10-16 | 2025-10-26
Expected | 2025-10-16 | 2025-10-21
15 - MGR: Clicking an account on the chart of accounts page should lead to the ledger page for the account where all entries can be viewed | 2025-10-16 | 2025-10-26
Expected | 2025-10-16 | 2025-10-21
16 - MGR: Each entry in the account ledger must have a clickable post reference column which will lead to the journal entry which created it | 2025-10-16 | 2025-10-25
Expected | 2025-10-16 | 2025-10-21
17 - MGR: The ledger page must show the date of the journal entry, a description column which is usually empty, a debit, a credit column, and a balance column. | 2025-10-16 | 2025-10-25
Expected | 2025-10-16 | 2025-10-21
18 - MGR: The ledger page must have filtering and search features. | 2025-10-16 | 2025-10-25
Expected | 2025-10-16 | 2025-10-21
19 - ACCT: Can create journal entries using only accounts found in the chart of accounts | 2025-10-16 | 2025-10-23
Expected | 2025-10-16 | 2025-10-21
20 - ACCT: Debits come before credits in each journal entry created | 2025-10-16 | 2025-10-21
Expected | 2025-10-16 | 2025-10-21
21 - ACCT: Multiple debits and multiple credits must be possible for each journal entry recorded | 2025-10-16 | 2025-10-21
Expected | 2025-10-16 | 2025-10-21
22 - ACCT: Must be able to attach source documents to each journal entry of type pdf, word, excel, csv, jpg, and png | 2025-10-16 | 2025-10-23
Expected | 2025-10-16 | 2025-10-21
23 - ACCT: Can cancel or reset a journal entry before it is submitted if restarting is desired but once a journal entry is submitted the accountant cannot delete it | 2025-10-16 | 2025-10-21
Expected | 2025-10-16 | 2025-10-21
24 - ACCT: Can prepare and submit journal entries | 2025-10-16 | 2025-10-23
Expected | 2025-10-16 | 2025-10-21
25 - ACCT: Can view journal entries created by the manager or other accountants | 2025-10-16 | 2025-10-23
Expected | 2025-10-16 | 2025-10-21
26 - ACCT: Can view the status of all journal entries submitted for approval with pending, approved, or rejected status | 2025-10-16 | 2025-10-23
Expected | 2025-10-16 | 2025-10-21
27 - ACCT: Must be able to filter journal entries displayed for pending, approved, and rejected categories by date | 2025-10-16 | 2025-10-23
Expected | 2025-10-16 | 2025-10-21
28 - ACCT: Must be able to search a journal by account name, amount, or date | 2025-10-16 | 2025-10-23
Expected | 2025-10-16 | 2025-10-21
29 - ACCT: View Event Logs | 2025-10-16 | 2025-10-23
Expected | 2025-10-16 | 2025-10-21
30 - ACCT: Must be able to click an account name to go to the ledger of the account | 2025-10-16 | 2025-10-23
Expected | 2025-10-16 | 2025-10-21
31 - ACCT: Once journal entry is approved, the entry must be reflected in the ledger for the account | 2025-10-16 | 2025-10-23
Expected | 2025-10-16 | 2025-10-21
32 - ACCT: From the ledger page, must be able to click the post reference (PR) to go to the journal entry which created the account | 2025-10-16 | 2025-10-23
Expected | 2025-10-16 | 2025-10-21
33 - ACCT: Each transaction must have at least one debit and one credit | 2025-10-16 | 2025-10-23
Expected | 2025-10-16 | 2025-10-21
34 - ACCT: Do not allow submitting of a transaction containing an error | 2025-10-16 | 2025-10-23
Expected | 2025-10-16 | 2025-10-21
35 - ACCT: Must be able to send email to the manager or the administrator from the account page | 2025-10-16 | 2025-10-23
Expected | 2025-10-16 | 2025-10-21
36 - ACCT: Total of debits in a journal entry must equal total of credits | 2025-10-16 | 2025-10-23
Expected | 2025-10-16 | 2025-10-21
37 - ACCT: Error messages must be housed in a database table | 2025-10-16 | 2025-10-23
Expected | 2025-10-16 | 2025-10-21
38 - ACCT: Error messages must be displayed in red color | 2025-10-16 | 2025-10-23
Expected | 2025-10-16 | 2025-10-21
39 - ACCT: Once root cause of error is corrected, error should go away | 2025-10-16 | 2025-10-23
Expected | 2025-10-16 | 2025-10-21
40 - ACCT: Manager must get notification when journal entry is submitted for approval | 2025-10-16 | 2025-10-23
Expected | 2025-10-16 | 2025-10-21
41 - ACCT: Clicking an account on the chart of accounts page should lead to the ledger page for the account where all entries can be viewed | 2025-10-16 | 2025-10-23
Expected | 2025-10-16 | 2025-10-21
42 - ACCT: Each entry in the account ledger must have a clickable post reference column which will lead to the journal entry which created it | 2025-10-16 | 2025-10-23
Expected | 2025-10-16 | 2025-10-21
43 - ACCT: Ledger UI design | 2025-10-16 | 2025-10-23
Expected | 2025-10-16 | 2025-10-21
44 - ACCT: Ledger filters and search | 2025-10-16 | 2025-10-23
Sprint 4
Expected | 2025-10-24 | 2025-11-04
1 - MGR: Can generate, view, save, email, or print financial sheets | 2025-10-24 | 2025-11-04
Expected | 2025-10-24 | 2025-10-26
2 - MGR: Approve or reject journal entries | 2025-10-24 | 2025-10-26
Expected | 2025-10-24 | 2025-11-04
3 - MGR: Approved journal entries must be reflected in ledger | 2025-10-24 | 2025-11-04
Expected | 2025-10-24 | 2025-10-26
4 - MGR: View all adjusting journal entries with pending status | 2025-10-24 | 2025-10-26
Expected | 2025-10-24 | 2025-10-26
5 - MGR: View all approved journal entries | 2025-10-24 | 2025-10-26
Expected | 2025-10-24 | 2025-10-26
6 - MGR: View all rejected journal entries | 2025-10-24 | 2025-10-26
Expected | 2025-10-24 | 2025-10-26
7 - MGR: Filter journal entries by date | 2025-10-24 | 2025-10-26
Expected | 2025-10-24 | 2025-10-26
8 - MGR: Search journal by account name, amount or date | 2025-10-24 | 2025-10-26
Expected | 2025-10-24 | 2025-10-26
9 - MGR: View event logs for each account | 2025-10-24 | 2025-10-26
Expected | 2025-10-24 | 2025-11-04
10 - MGR: Click account name or number to go to ledger of account | 2025-10-24 | 2025-11-04
Expected | 2025-10-24 | 2025-11-04
11 - MGR: Click PR in ledger to go to corresponding journal entry | 2025-10-24 | 2025-11-04
Expected | 2025-10-24 | 2025-10-26
12 - ACCT: Create adjusting jounral entries using only accounts only in COA | 2025-10-24 | 2025-10-26
Expected | 2025-10-24 | 2025-11-04
13 - ACCT: Attach source documents to each journal entry | 2025-10-24 | 2025-11-04
Expected | 2025-10-24 | 2025-10-26
14 - ACCT: Cancel or reset entry but once submitted cannot be deleted | 2025-10-24 | 2025-10-26
Expected | 2025-10-24 | 2025-10-26
15 - ACCT: Can prepare and submit journal entries | 2025-10-24 | 2025-10-26
Expected | 2025-10-24 | 2025-10-27
16 - ACCT: Can view journal entries created by manager or other accountant | 2025-10-24 | 2025-10-27
Expected | 2025-10-24 | 2025-10-27
17 - ACCT: View status of journal entries | 2025-10-24 | 2025-10-27
Expected | 2025-10-24 | 2025-11-04
18 - ACCT: Filter journal entries by date | 2025-10-24 | 2025-11-04
Expected | 2025-10-24 | 2025-11-04
19 - ACCT: Search journal by account name, amount or date | 2025-10-24 | 2025-11-04
Expected | 2025-10-24 | 2025-11-04
20 - ACCT: View event logs for each account in COA | 2025-10-24 | 2025-11-09
Expected | 2025-10-24 | 2025-11-04
21 - ACCT: Click account name or number to go to ledger of that account | 2025-10-24 | 2025-11-04
Expected | 2025-10-24 | 2025-11-04
22 - ACCT: Approved journal entries must be reflected in ledger and financial statements | 2025-10-24 | 2025-11-04
Expected | 2025-10-24 | 2025-11-04
23 - ACCT: Click PR in ledger to go to corresponding journal entry | 2025-10-24 | 2025-11-04
Expected | 2025-10-24 | 2025-10-24
24 - ACCT: Each transaction must have at least one debit and one credit | 2025-10-24 | 2025-10-24
Expected | 2025-10-24 | 2025-10-25
25 - ACCT: Cannot submit transaction with error | 2025-10-24 | 2025-10-25
Expected | 2025-10-24 | 2025-11-04
26 - ACCT: Send email to manager or admin from account page | 2025-10-24 | 2025-11-04
Expected | 2025-10-24 | 2025-10-25
27 - ACCT: Total of debits must equal total of credits otherwise error message must be displayed | 2025-10-24 | 2025-10-25
Expected | 2025-10-24 | 2025-11-04
28 - Error messgaes housed in DB | 2025-10-24 | 2025-11-08
Expected | 2025-10-24 | 2025-10-25
29 - Error messages displayed in red | 2025-10-24 | 2025-10-25
Expected | 2025-10-24 | 2025-10-25
30 - ACCT: Once root cause of error is corrected, error should go away | 2025-10-24 | 2025-10-25
Expected | 2025-10-24 | 2025-11-04
31 - ACCT: Manager must get notification when entry is submitted for approval | 2025-10-24 | 2025-11-04
Expected | 2025-10-24 | 2025-11-04
32 - ACCT: Clicking account name or number on account page should lead to corresponding edger | 2025-10-24 | 2025-11-04
Expected | 2025-10-24 | 2025-11-04
33 - ACCT: Each entry in ledger must have clickable PR | 2025-10-24 | 2025-11-04
Expected | 2025-10-24 | 2025-11-04
34 - ACCT: Ledger page must show date of entry, description column, debit & credti, and balance | 2025-10-24 | 2025-11-04
Expected | 2025-10-24 | 2025-11-04
35 - ACCT: Ledger page must have filtering | 2025-10-24 | 2025-11-04
Sprint 5
Expected | 2025-11-04 | 2025-11-14
1 - View financial ratios on landing page | 2025-11-04 | 2025-11-14
Expected | 2025-11-04 | 2025-11-14
2 - Buttons to other services must be found on landing page (role based) | 2025-11-04 | 2025-11-14
Expected | 2025-11-04 | 2025-11-18
3 - Display important messages on landing page | 2025-11-04 | 2025-11-18
Expected | 2025-11-04 | 2025-11-18
4 - Dashboard must display using three colors -- green, red, yellow | 2025-11-04 | 2025-11-18
Expected | 2025-11-04 | 2025-11-18
5 - Look and feel of landing page must be consistant with other pages | 2025-11-04 | 2025-11-18

## Help
Project Start Date | 2024-01-01
Days Per Column | 7
Instructions
1. Update "Project Start Date" and "Days Per Column" above.
2. Update the gantt chart rows with task names, start dates, and end dates.
3. The template will automatically fill the gantt chart bars.
Provided By
onlinegantt.com - Free Online Gantt Chart Software